## Tablib Dataset
id | project_id | user_id | user_as_sales_teamlead | user_email | project_director | project_hod | project_manager | project_teamlead | sales_owner | project_code | name | project_type | sample | clients | cpi | set_up_fee | transaction_fee | other_cost | operation_team | operation_select | finance_team | finance_select | upload_document | tentative_start_date | tentative_end_date | estimated_time | status | remark | man_days | reason_for_adjustment | send_email_manager | total_achievement | remaining_time | remaining_interview | is_active | created_at | updated_at
105 |  | 36 | 36 | pawankumar@novusinsights.com | 1 | 4 | 10 | 9 |  | 085vsa186 | project001 | 1 | 120 | 85 | 2 | 1 |  |  |  | 1 |  | 0 |  | 2024-07-15 00:00:00 | 2024-07-27 00:00:00 | 12 days, 0:00:00 | inprogress | project_start_by_operation_team | 5 |  | 0 | 20 | 9 days, 8:00:00 | 100 | 0 | 2024-07-15 12:17:28 | 2024-07-15 12:25:23
104 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 8 |  |  | 001glg107 | Qual0000-0001Shippers ¦ Unimrkt | 1 | 80 | 1 | 20 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-08 00:00:00 | 2024-07-15 00:00:00 | 7 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:19 | 2024-07-15 11:19:19
94 |  | 8 | 8 | saransh.sharma@unimrkt.com |  |  | 3 |  |  | 003pot108 | Energy Management software | 3 | 3 | 3 | 38 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-03 00:00:00 | 2024-07-05 00:00:00 | 2 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:19 | 2024-07-15 11:19:19
93 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg109 | SPECT Market Assessment 2024: GLG Feasibility Requ | 3 | 49 | 1 | 54 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-03 00:00:00 | 2024-07-26 00:00:00 | 23 days, 0:00:00 | inprogress | project_start_by_operation_team | 3.25 |  | 0 | 22 | 14 days, 22:00:00 | 27 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:06:11
92 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 010cin110 | JC1050- Maritime Cybersecurity DMs | 3 | 100 | 10 | 58 | 200 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-11 00:00:00 | 9 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:19 | 2024-07-15 11:19:19
91 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg111 | Project Bid- Advisory and Consulting Survey | 3 | 50 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-26 00:00:00 | 24 days, 0:00:00 | inprogress | project_start_by_operation_team | 2.75 |  | 0 | 20 | 19 days, 2:00:00 | 30 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:05:37
90 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 5 | 15 |  | 005rot112 | New project - PMIS | 3 | 100 | 5 | 44 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-12 00:00:00 | 10 days, 0:00:00 | inprogress | project_start_by_operation_team | 10 |  | 0 | 86 | -1 day, 16:00:00 | 14 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:05:14
89 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg113 | 2 New Bids: Med Tech | 3 | 10 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-05 00:00:00 | 3 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:19 | 2024-07-15 11:19:19
88 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg114 | Semiconductor Survey June 2024) | 3 | 35 | 1 | 58 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-15 00:00:00 | 13 days, 0:00:00 | completed | project_start_by_operation_team | 4 |  | 0 | 35 | 6 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:04:41
87 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg115 | Air Pollution Control Solutions - 2 (Survey #60455 | 3 | 35 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-19 00:00:00 | 17 days, 0:00:00 | inprogress | project_start_by_operation_team | 4.75 |  | 0 | 29 | 11 days, 10:00:00 | 6 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:04:06
86 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg116 | Customers of HVAC/Cooling Distribution Add on samp | 3 | 18 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-12 00:00:00 | 10 days, 0:00:00 | completed | project_start_by_operation_team | 0 |  | 0 | 0 | 4 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:03:40
85 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 4 | 7 |  |  | 003pot117 | Accounting software | 3 | 30 | 3 | 38 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-08 00:00:00 | 6 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:19 | 2024-07-15 11:19:19
84 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg118 | Fashion E-Commerce (July 2024) | 3 | 50 | 1 | 58 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-26 00:00:00 | 24 days, 0:00:00 | inprogress | project_start_by_operation_team | 3.25 |  | 0 | 20 | 18 days, 22:00:00 | 30 | 0 | 2024-07-15 11:19:19 | 2024-07-16 13:03:05
83 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg119 | IT Resellers 2024 (July 2024) | 3 | 8 | 1 | 54 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-12 00:00:00 | 10 days, 0:00:00 | to_be_started |  | 0 | NA | 0 | 0 | 7 days, 0:00:00 |  | 0 | 2024-07-15 11:19:20 | 2024-07-15 11:19:20
82 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg120 | CIAM Experts | 3 | 30 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-19 00:00:00 | 17 days, 0:00:00 | inprogress | project_start_by_operation_team | 0.75 |  | 0 | 5 | 12 days, 18:00:00 | 25 | 0 | 2024-07-15 11:19:20 | 2024-07-16 13:02:33
81 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg121 | Tech Grown Intl Survey | 3 | 20 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-19 00:00:00 | 17 days, 0:00:00 | inprogress | project_start_by_operation_team | 1.5 |  | 0 | 10 | 8 days, 18:00:00 | 15 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:58:48
80 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 4 |  |  | 002sym122 | SYM2401409 BuilderSeries 2024 (July Wave) | 3 | 100 | 2 | 43 | 200 |  |  |  | 1 |  | 0 |  | 2024-07-02 00:00:00 | 2024-07-11 00:00:00 | 9 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 0:00:00 |  | 0 | 2024-07-15 11:19:20 | 2024-07-15 11:19:20
79 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg123 | Marketing Roles/Investment Survey | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-01 00:00:00 | 2024-07-19 00:00:00 | 18 days, 0:00:00 | inprogress | project_start_by_operation_team | 3 |  | 0 | 24 | 12 days, 0:00:00 | 26 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:58:12
78 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg124 | IBM Platinum Partners (July 2024) | 3 | 24 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-01 00:00:00 | 2024-07-25 00:00:00 | 24 days, 0:00:00 | completed | project_start_by_operation_team | 3.25 | NA | 0 | 22 | 20 days, 22:00:00 | 2 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:57:35
77 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg125 | Pest Control Trends April 2024 (Wave 3) | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-01 00:00:00 | 2024-07-26 00:00:00 | 25 days, 0:00:00 | completed | project_start_by_operation_team | 6.5 | on hold | 0 | 50 | 20 days, 20:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:55:12
76 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg126 | Locomotives and Railcar Survey - Re-run (July 2024 | 3 | 25 | 1 | 54 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-01 00:00:00 | 2024-07-08 00:00:00 | 7 days, 0:00:00 | completed | project_start_by_operation_team | 4.5 |  | 0 | 25 | 3 days, 12:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:54:42
75 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg127 | US Insurance Carriers | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-07-01 00:00:00 | 2024-07-25 00:00:00 | 24 days, 0:00:00 | inprogress | project_start_by_operation_team | 5.5 | NA | 0 | 38 | 20 days, 4:00:00 | 12 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:53:42
74 |  | 22 | 22 | pawankumar@novusinsights.com |  | 3 | 10 | 9 |  | 001glg128 | test-project001 | 2 | 400 | 1 | 100 | 100 |  |  |  | 1 |  | 0 |  | 2024-06-20 00:00:00 | 2024-07-19 00:00:00 | 29 days, 0:00:00 | to_be_started | project_start_by_operation_team | 2 | as my own business | 0 | 11 | 27 days, 8:00:00 | 189 | 0 | 2024-07-15 11:19:20 | 2024-07-15 11:19:20
73 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg129 | Real Estate Brokers | 3 | 70 | 1 | 48 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-12 00:00:00 | 31 days, 0:00:00 | completed | project_start_by_operation_team | 8.75 |  | 0 | 70 | 26 days, 2:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:53:01
72 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg130 | European Biogas Industry | 3 | 46 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-17 00:00:00 | 36 days, 0:00:00 | inprogress | project_start_by_operation_team | 1.5 |  | 0 | 10 | 32 days, 12:00:00 | 36 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:52:15
71 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg131 | Audit Management & Certification Software | 3 |  | 1 | 40 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-12 00:00:00 | 31 days, 0:00:00 | completed | project_start_by_operation_team | 7.5 |  | 0 | 50 | 26 days, 12:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:51:42
70 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg132 | Voice of Customer Survey - 603815 | 3 | 37 | 1 | 50 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-11 00:00:00 | 30 days, 0:00:00 | completed | project_start_by_operation_team | 4.75 | NA | 0 | 37 | 26 days, 10:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:51:01
69 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg133 | Customers of HVAC/Cooling Distribution - June 2024 | 3 | 18 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-17 00:00:00 | 36 days, 0:00:00 | inprogress | project_start_by_operation_team | 0.75 |  | 0 | 5 | 33 days, 18:00:00 | 13 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:50:33
68 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg134 | Fractional Aircraft Owners Survey Request | 3 | 150 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-31 00:00:00 | 50 days, 0:00:00 | inprogress | project_start_by_operation_team | 19 | na | 0 | 119 | 41 days, 16:00:00 | 31 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:50:01
67 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg135 | Gen AI purchasers from a company list | 3 |  | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-04 00:00:00 | 23 days, 0:00:00 | to_be_started |  | 0 |  | 0 | 0 | 15 days, 0:00:00 |  | 0 | 2024-07-15 11:19:20 | 2024-07-15 11:19:20
66 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg136 | Understanding Interest in Health Hardware Benefit | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-10 00:00:00 | 29 days, 0:00:00 | completed | project_start_by_operation_team | 4.5 | NA | 0 | 27 | 25 days, 12:00:00 | 23 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:49:31
65 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg137 | Legal Software | 3 |  | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-11 00:00:00 | 2024-07-12 00:00:00 | 31 days, 0:00:00 | completed | project_start_by_operation_team | 4 |  | 0 | 26 | 28 days, 16:00:00 | 9 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:49:06
64 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg138 | Generative AI Value (Survey #603910) | 3 |  | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-07-12 00:00:00 | 37 days, 0:00:00 | completed | project_start_by_operation_team | 5.25 |  | 0 | 39 | 28 days, 6:00:00 | 0 | 0 | 2024-07-15 11:19:20 | 2024-07-16 12:48:34
63 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg139 | E-Commerce Merchant Sales Expansion Trends | 3 |  | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-07-12 00:00:00 | 37 days, 0:00:00 | completed | project_start_by_operation_team | 4 |  | 0 | 40 | 33 days, 16:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:48:05
62 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg140 | Legal Practice Management Solutions | 3 | 55 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-07-12 00:00:00 | 37 days, 0:00:00 | completed | project_start_by_operation_team | 2.5 |  | 0 | 55 | 34 days, 4:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:47:38
61 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg141 | Logistics Survey - June 24 (Survey #) | 3 | 54 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-07-12 00:00:00 | 37 days, 0:00:00 | completed | project_start_by_operation_team | 7 |  | 0 | 54 | 3 days, 16:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:46:44
60 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg142 | ERP Users Poland (Survey #) May 2024 | 3 |  | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-07-04 00:00:00 | 29 days, 0:00:00 | completed | project_start_by_operation_team | 1.25 |  | 0 | 12 | 26 days, 14:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:46:14
59 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg143 | Accounting and Tax Firms ERP - PL | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-05 00:00:00 | 2024-06-17 00:00:00 | 12 days, 0:00:00 | completed | project_start_by_operation_team | 1 |  | 0 | 7 | 9 days, 16:00:00 | 43 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:45:41
58 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg144 | Roofing-Unimrkt | 3 | 54 | 1 | 48 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-03 00:00:00 | 2024-07-12 00:00:00 | 39 days, 0:00:00 | completed |  | 8.5 |  | 0 | 54 | 35 days, 0:00:00 | 0 | 1 | 2024-07-15 11:19:21 | 2024-07-16 12:18:28
57 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg145 | Warehouse Trends | 3 | 28 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-03 00:00:00 | 2024-07-04 00:00:00 | 31 days, 0:00:00 | to_be_started | project_start_by_operation_team | 4.5 |  | 0 | 28 | 26 days, 12:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-15 11:19:21
56 |  | 26 | 26 | pawan.mishra@novusinsights.com |  | 3 | 10 | 9 |  | 002sym146 | test | 2 | 100 | 2 | 1 | 1 |  |  |  | 1 |  | 0 |  | 2024-05-31 00:00:00 | 2024-06-21 00:00:00 | 21 days, 0:00:00 | to_be_started | project_start_by_operation_team | 2.5 |  | 0 | 21 | 19 days, 4:00:00 | 79 | 0 | 2024-07-15 11:19:21 | 2024-07-15 11:19:21
55 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg147 | POS Home Improvement | 3 | 30 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-31 00:00:00 | 2024-06-11 00:00:00 | 11 days, 0:00:00 | completed | project_start_by_operation_team | 2 |  | 0 | 16 | 5 days, 8:00:00 | 14 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:17:38
54 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg148 | Financial Institutions Software | 3 | 17 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-29 00:00:00 | 2024-07-12 00:00:00 | 44 days, 0:00:00 | completed | project_start_by_operation_team | 2 |  | 0 | 17 | 37 days, 8:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:16:57
53 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg149 | Commercial/Business Digital Banking Software-Unimr | 3 | 17 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-29 00:00:00 | 2024-07-04 00:00:00 | 36 days, 0:00:00 | completed | project_start_by_operation_team | 2.5 | completed | 0 | 17 | 29 days, 4:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:16:28
52 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg150 | Certiport, CertiPREP, and PVTCs | 3 | 25 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-06 00:00:00 | 2024-07-17 00:00:00 | 41 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 47 days, 0:00:00 |  | 0 | 2024-07-15 11:19:21 | 2024-07-15 11:19:21
51 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg151 | Roofing Market Trends | 3 | 102 | 1 | 48 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-27 00:00:00 | 2024-07-12 00:00:00 | 46 days, 0:00:00 | inprogress |  | 13.5 |  | 0 | 77 | 60 days, 0:00:00 | 0 | 1 | 2024-07-15 11:19:21 | 2024-07-16 12:15:46
50 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg152 | Feasibility Estimate for Value Added Reseller Stud | 3 | 10 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-29 00:00:00 | 2024-07-12 00:00:00 | 44 days, 0:00:00 | inprogress |  | 1 |  | 0 | 0 | 38 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:15:10
49 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg153 | Pool Dealers (May 2024) | 3 |  | 1 | 52 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-24 00:00:00 | 2024-07-31 00:00:00 | 68 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 62 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-15 11:19:21
48 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg154 | Software Space - Jun 24 (Survey #) | 3 | 64 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-27 00:00:00 | 2024-07-17 00:00:00 | 51 days, 0:00:00 | onhold |  | 10 |  | 0 | 48 | 40 days, 0:00:00 | 16 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:14:13
47 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg155 | Payor Survey-Unimrkt | 3 | 20 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-23 00:00:00 | 2024-06-15 00:00:00 | 23 days, 0:00:00 | completed |  | 2 |  | 0 | 20 | 10 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:13:38
46 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg156 | Network Survey- Heat Pump Market II | 3 | 60 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-23 00:00:00 | 2024-07-12 00:00:00 | 50 days, 0:00:00 | inprogress |  | 10 |  | 0 | 20 | 36 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:21 | 2024-07-16 12:13:08
45 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg157 | Network Survey - Hospital Management Software | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-22 00:00:00 | 2024-06-12 00:00:00 | 21 days, 0:00:00 | completed |  | 13 |  | 0 | 46 | 9 days, 0:00:00 | 4 | 0 | 2024-07-15 11:19:22 | 2024-07-16 12:10:05
44 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg158 | US Power Finance DMs | 3 | 74 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-06-12 00:00:00 | 2024-07-17 00:00:00 | 35 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 47 days, 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
43 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg159 | OEM & System Integrator Study - PSF TEAM | 3 | 299 | 1 | 40 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-29 00:00:00 | 2024-07-31 00:00:00 | 63 days, 0:00:00 | inprogress | project_start_by_operation_team | 4.5 |  | 0 | 27 | 21 days, 0:00:00 | 23 | 0 | 2024-07-15 11:19:22 | 2024-07-16 12:09:24
42 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg160 | Restaurant Benefits Managers Survey | 3 | 54 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-23 00:00:00 | 2024-07-12 00:00:00 | 50 days, 0:00:00 | completed | project_start_by_operation_team | 6.75 |  | 0 | 54 | 30 days, 3:06:07.178744 | 0 | 0 | 2024-07-15 11:19:22 | 2024-07-16 12:06:41
41 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg161 | Financial Services Solutions Survey (Survey #60346 | 3 | 80 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  |  |  | 11 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-16 12:06:11
40 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg162 | Aviation Repair and Maintenance survey Wave# 8 | 3 | 66 | 1 | 56 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-20 00:00:00 | 2024-07-31 00:00:00 | 72 days, 0:00:00 | inprogress | project_start_by_operation_team | 10 |  | 0 | 50 | 17 days, 16:00:00 | 16 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:42:00
39 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg163 | Independent Chainsaw Retailers | 3 | 50 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-21 00:00:00 | 2024-05-31 00:00:00 | 10 days, 0:00:00 | completed | project_start_by_operation_team | 6 |  | 0 | 50 | 0:00:00 | 0 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:41:24
38 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg164 | MMSI Market Assessment (May 2024) | 3 | 40 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-20 00:00:00 | 2024-05-24 00:00:00 | 4 days, 0:00:00 | completed |  | 4 |  | 0 | 15 | 0:00:00 | 25 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:40:45
37 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg165 | Network Survey- Waste Management | 3 | 46 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-21 00:00:00 | 2024-05-30 00:00:00 | 9 days, 0:00:00 | completed |  |  |  | 0 |  | -1 day, 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:40:08
36 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 |  |  | 001glg166 | Pharmacy ERP Software Solutions | 3 | 20 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-20 00:00:00 | 2024-05-24 00:00:00 | 4 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
35 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg167 | Research & Insights Survey | 3 | 100 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-17 00:00:00 | 2024-06-04 00:00:00 | 18 days, 0:00:00 | completed | project_start_by_operation_team | 8.25 |  | 0 | 65 | 3 days, 6:00:00 | 35 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:38:44
34 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg168 | Automotive Dealers | 3 | 24 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-16 00:00:00 | 2024-07-12 00:00:00 | 57 days, 0:00:00 | completed | project_start_by_operation_team | 3.25 |  | 0 | 24 | 41 days, 22:00:00 | 0 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:38:15
33 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg169 | Global Financial Insights | 3 | 75 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-16 00:00:00 | 2024-06-03 00:00:00 | 18 days, 0:00:00 | to_be_started | project_start_by_operation_team | 9.5 |  | 0 | 47 | -2 days, 20:00:00 | 28 | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
32 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg170 | Identity Solution Insights | 3 | 50 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-20 00:00:00 | 2024-05-27 00:00:00 | 7 days, 0:00:00 | completed | project_start_by_operation_team | 9 |  | 0 | 32 | -1 day, 0:00:00 | 18 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:37:42
31 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg171 | The Future of Groceries 2nd Annual Survey (Survey | 3 | 88 | 1 | 54 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-16 00:00:00 | 2024-06-03 00:00:00 | 18 days, 0:00:00 | completed | project_start_by_operation_team | 10 |  | 0 | 78 | -2 days, 16:00:00 | 10 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:37:16
30 |  | 8 | 8 | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 7 |  | 001glg172 | Life Sciences/Services Survey Request - Target Lis | 3 | 3 | 1 | 25 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-17 00:00:00 | 2024-05-31 00:00:00 | 14 days, 0:00:00 | completed | edit through nishant arora email | 3 |  | 0 | 3 | -3 days, 0:00:00 | 0 | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:34:55
27 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg173 | project13 | 1 | 3212 | 1 | 123 | 112 |  |  |  | 1 |  | 0 |  | 2024-05-15 00:00:00 | 2024-07-25 00:00:00 | 71 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
25 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 8 |  | 001glg174 | Network Survey- Resins Furniture Trends | 3 | 40 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-14 00:00:00 | 2024-05-21 00:00:00 | 7 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 1 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
24 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg175 | Agricultural Technology | 3 | 30 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-13 00:00:00 | 2024-05-21 00:00:00 | 8 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
23 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg176 | Texas Finance DMs | 3 | 200 | 1 | 52 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-13 00:00:00 | 2024-05-27 00:00:00 | 14 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-15 11:19:22
22 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg177 | Chief Sustainability Officers | 3 | 10 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-10 00:00:00 | 2024-05-15 00:00:00 | 5 days, 0:00:00 | to_be_started |  |  |  | 0 |  | 0:00:00 |  | 0 | 2024-07-15 11:19:22 | 2024-07-16 11:33:51
21 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 6 |  | 001glg178 | Acid-Etched Glass | 3 | 100 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-07 00:00:00 | 2024-05-28 00:00:00 | 21 days, 0:00:00 | completed | project_start_by_operation_team | 15.75 |  | 0 | 100 | 7 days, 18:00:00 | 0 | 1 | 2024-07-15 11:19:23 | 2024-07-16 11:33:19
20 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 2 | 8 | 7 |  | 001glg179 | Contact Center/Unified Comms | 3 | 80 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-08 00:00:00 | 2024-06-14 00:00:00 | 37 days, 0:00:00 | onhold |  | 10 |  | 1 | 13 | 11 days, 0:00:00 | 67 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:32:45
18 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 9 | 7 |  | 001glg180 | Independent Restaurant Owners in US - Survey Reque | 3 | 50 | 1 | 48 | 0 |  |  |  | 1 |  | 0 |  | 2024-04-30 00:00:00 | 2024-05-13 00:00:00 | 13 days, 0:00:00 | completed |  |  |  | 0 | 43 | 4 days, 8:00:00 | 7 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:36:41
17 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 2 | 8 | 7 |  | 001glg181 | Food Mftg Survey Request | 3 | 100 | 1 | 53 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-06 00:00:00 | 2024-06-18 00:00:00 | 43 days, 0:00:00 | onhold | project_start_by_operation_team | 3 |  | 1 | 14 | 22 days, 8:00:00 | 86 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:31:24
14 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg182 | eSentire Customers CATI | 3 | 100 | 1 | 51 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-02 00:00:00 | 2024-05-24 00:00:00 | 22 days, 0:00:00 | inprogress | project_start_by_operation_team | 24 |  | 0 | 71 | -3 days, 0:00:00 | 29 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:30:54
12 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg183 | Advertising in Mobile Gaming | 3 | 30 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-02 00:00:00 | 2024-05-23 00:00:00 | 21 days, 0:00:00 | inprogress | project_start_by_operation_team | 16 |  | 0 | 28 | 11 days, 0:00:00 | 2 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:30:21
11 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg184 | Price CheX: Industry Cameras << 602993 | 3 | 100 | 1 | 49 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-02 00:00:00 | 2024-05-25 00:00:00 | 23 days, 0:00:00 | inprogress | project_start_by_operation_team | 2 |  | 0 | 2 | 7 days, 8:00:00 | 98 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:29:48
10 |  | 8 |  | saransh.sharma@unimrkt.com | 1 | 1 | 1 | 2 |  | 001glg185 | Network Survey- Semiconductors Supply Chain III | 3 | 50 | 1 | 56 | 0 |  |  |  | 1 |  | 0 |  | 2024-05-02 00:00:00 | 2024-05-24 00:00:00 | 22 days, 0:00:00 | inprogress | project_start_by_operation_team | 4 |  | 0 | 21 | 0:00:00 | 29 | 0 | 2024-07-15 11:19:23 | 2024-07-16 11:29:13